## Remaining SOW
bug_id | target_milestone | bug_severity | priority | op_sys | assigned_to | bug_status | resolution | short_desc | estimated_time | deadline |  | Review in PMI Mtg. | Granular Priortization | Team Review | Part | Module | Collector Bugs feeding into 6033 | Blocking other bug
4171 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | PEXPRESS | --- | ALL OVER in ISO TC213 | 40 | ? |  |  |  |  | 47 | Shape Variation Tolerances | 6183
4452 | CR_PMI_3 | enhancement | P2 | Internal | pierre.duchier@airbus.com | CONFIRMED | --- | "Direction feature" from ISO 1101:2012 | ? | ? |  |  |  |  | 1051 | Geometric Tolerance
4386 | CRx PMI-2 | general | P2 | Internal | richard.s.zuray@boeing.com | CONFIRMED | --- | Collector: Proposed Scope for Next PMI Work | 0 | [5 empty] | AP242 general |  | NA
3889 | CR_PMI_3 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | --- | Presentable text from non-presentation entities | 100 | 2017-04-30 |  | X
5032 | CR_PMI_3 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | --- | add design model uncertainty to STEP | 2 | 2017-04-14
4817 | CRx PMI-2 | enhancement | P4 | Internal | brandon.sapp@boeing.com | CONFIRMED | --- | Rule draughting_model_items_constraint: draughting_annotation_occurrence & draughting_elements | 2 | 2017-03-27
5899 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | CONFIRMED | --- | Allow shells for surface models in construction geometry | 0
6201 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | CONFIRMED | --- | Collector bug for AM 1051 Geometric_tolerance for CRx_PMI 2 | 0 | [5 empty] | 1051 | Geometric Tolerance | 6201
6044 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | --- | Collector bug for part 113 | 0 | [5 empty] | 113 | Mechnical design application resource | 6044
6045 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | --- | Collector bug for AM 1362 Dimension and tolerance callouts for bug 5006 | 0 | [5 empty] | 1362 | Dimension and tolerance callouts | 6045
6203 | CR_Geometry_2 | enhancement | P4 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | --- | Write a rule for Styled_element.appearance | 0
3701 | CRx PMI-2 | enhancement | P1 | Internal | claudia.c.huebner@boeing.com | IN_PROGRESS | --- | spotface dimension discussion | 0 |  |  | x |  |  | 1814 | Machining Features | 6044
6208 | CRx PMI-2 | enhancement | P1 | Internal | thomas.r.thurman@imonmail.com | RESOLVED | DUPLICATE | Collector: New AM Mechanical_design | 40 | 2017-04-28 |  |  |  |  | SMRL |  | NA
3701 | CR_PMI_3 | enhancement | P2 | Internal | claudia.c.huebner@boeing.com | IN_PROGRESS | --- | Flag Notes are not supported in STEP | 0 | 2017-03-31 |  | x
6183 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | IN_PROGRESS | --- | Collector bug for Part 47 for CRx PMI-2 | 0 | [5 empty] | 47 | Shape Variation Tolerances | 6183
3727 | CR_PMI_3 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | IN_PROGRESS | --- | where rules too restrictive for draughting annotation occurrence | 8 | 2017-05-05 |  |  |  |  | 506 | Draughting Annotation
5017 | CR_PMI_3 | minor technical | P2 | Ballot Comment | thomas.r.thurman@imonmail.com | PEXPRESS | --- | between_shape_aspect constraints needed | 0 | 2017-03-24 |  | x |  |  | 47 | Shape Variation Tolerances
5529 | CR_Geometry_2 | normal | P4 | Internal | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Add surface visual texture module | 0
5530 | CR_Geometry_2 | major technical | P4 | Informal Implementer Review | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Too restrictive constraining of tessellated_item | 0
5842 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Collector bug for Part 46 for CR_Geometry 2 | 0
5844 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Add module for colour on vertices | 0
6032 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Collector bug for CR_Geometry_2 | 0
6039 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | IN_PROGRESS | --- | Collector bug for Part 42 Ed 6 for CR_Geometry 2 | 0
5553 | CRx PMI-2 | normal | P2 | Internal | richard.s.zuray@boeing.com | IN_PROGRESS | --- | collector bug for part41 for CRx PMI2 | 0 | [5 empty] | 41 | Fundamentals of product description and support | 5553
6041 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | IN_PROGRESS | --- | Collector bug for P101 for CRx PMI 2 | 0 | [5 empty] | 101 | Draughting | 6041
6046 | CR_Geometry_2 | enhancement | P4 | Internal | thomas.r.thurman@imonmail.com | IN_PROGRESS | --- | Collector bug for Part 43 Ed 4 for CR_Geometry 2 | 0
3551 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | FIXED | Diameter for Datum Target Point and - Line ? | 4 | 2017-05-12 | Complete |  |  |  | 1051 | Geometric Tolerance | ??
3968 | CRx PMI-2 | enhancement | P2 | Internal | thomas.hedberg@nist.gov | RESOLVED | REMIND | How to relate datum/_system with TEDs? | 4 | 2017-03-31 |  |  |  |  | GD&T |  | NA
2962 | CR_PMI_3 | normal | P2 | Internal | thomas.r.thurman@imonmail.com | RESOLVED | FIXED | pre_defined_terminator_symbol and symbol_target | 4 | 2017-06-01 |  |  |  |  | 1003 | Curve Appearance | NA
3762 | CRx PMI-2 | enhancement | P5 | Internal | kahunten@gmail.com | RESOLVED | DUPLICATE | Situation and associated features | 0
3974 | CRx PMI-2 | enhancement | P5 | Internal | kahunten@gmail.com | RESOLVED | DUPLICATE | Runout tolerance verification | 0
5610 | CR_Geometry_2 | enhancement | P4 | Internal | kahunten@gmail.com | RESOLVED | DUPLICATE | Spelling error camera_model_d3_multi_clipping_inter(s)ection_select | 0
5838 | CR_Geometry_2 | enhancement | P4 | Internal | kahunten@gmail.com | RESOLVED | FIXED | Tessellated shape rep additional tessellation accuracy | 0
5964 | CRx PMI-2 | enhancement | P4 | Internal | kahunten@gmail.com | RESOLVED | INVALID | Datum.WR4 seems useless | 0
5907 | CR_PMI_3 | enhancement | P2 | Internal | brandon.sapp@boeing.com | NEW | --- | add AOs to Value_with_unit_extension AM | 40 | 2017-04-28 |  |  |  |  | 1753 | Value with unit extension
3675 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | IN_PROGRESS | --- | Overriding geometric tolerances (ALL OVER, ALL AROUND, default) | ? | ? |  | x |  |  | 1051 | Geometric Tolerance | ??
3789 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | IN_PROGRESS | --- | Globally-Applicable Specifications | ? | ? |  | x |  |  | GD&T |  | NA
5212 | CR_PMI_3 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | NEW | --- | Split AM 1721 to eliminate electrical domain context | 40 | 2017-04-28 |  | x
5908 | CR_PMI_3 | normal | P2 | Internal | thomas.r.thurman@imonmail.com | NEW | --- | Split AO General_feature into own Application module | 0 | 2017-04-07
5909 | CR_PMI_3 | normal | P2 | Internal | thomas.r.thurman@imonmail.com | NEW | --- | New AM General_feature module | 0 | 2017-04-07
5910 | CR_PMI_3 | normal | P2 | Internal | thomas.r.thurman@imonmail.com | NEW | --- | Do we need to extract apparently generic AOs from AM 1814 Machining features into a new AM? | 0 | 2017-04-07
6043 | CRx PMI-2 | normal | P4 | Internal | thomas.r.thurman@imonmail.com | VERIFIED | DUPLICATE | Collector bug for add Mechanical design application resource | 0
3702 | CRx PMI-2 | enhancement | P1 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS | --- | countersunk/counterbore/hole depth discussion | 0 | 2017-03-24 |  | x |  |  | GD&T |  | 6044
6141 | CRx PMI-2 | normal | P1 | Internal | richard.s.zuray@boeing.com | TREVIEW | --- | AM 1032 Shape_property_assignment Remove geometric_item_specific_usage.ur1 to support bug #5902 | 0 | 2017-05-19 |  |  |  | 2017-05-31 | 1032 | Shape Property Assignment | NA
6042 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | change draughting_callout_element to extensible generic_entity SELECT to allow extension in part 113 for bug 5006. | 12 | 2017-05-05 |  |  |  |  | 101 | Draughting | 6041
5902 | CRx PMI-2 | minor technical | P2 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS | --- | IIRU and GISU uniqueness rules | 0 | 2017-05-05 |  |  |  |  | 41 | Fundamentals of product description and support | 5553
4251 | CRx PMI-2 | minor technical | P2 | Ballot Comment | brandon.sapp@boeing.com | PDOCS | --- | AM 0442 Remove Global Rule RULE draughting_model_items_constraint | 4 | 2017-03-27 |  |  |  |  | 1362 | Dimension and tolerance callouts | 6045
5006 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS | --- | New annotation_occurrence subtype to support "Minimal Presentation" for PMI | 8 | 2017-05-19 |  |  |  |  | 113 | Mechanical design application resource | 6044, 6041
5144 | CR_PMI_3 | normal | P2 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS | --- | Assembly_bond_definition.bonded_feature_1, 2 problems. | 12 | 2017-05-19 |  |  |  |  | 1649 | Assembly Technology
5915 | CRx PMI-2 | normal | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Non uniform tolerance zone inconsistency | 8 | 2017-06-08 |  |  |  |  | 47 | Shape Variation Tolerances | 6183
6202 | CRx PMI-2 | normal | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Add Non uniform tolerance zone rule to AM Geometric_tolerance | 4 | 2017-05-26 |  |  |  |  | 1051 | Geometric Tolerance | 6201
4800 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PEXPRESS | --- | context_dependent_over_riding_styled_item.WR1 | 0
6186 | CR_Geometry_2 | enhancement | P4 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS | --- | Change Styled_element.appearance to reflect change in styled_item.styles in p46 | 0
4969 | CRx PMI-2 | normal | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | ISO 14660-1 withdrawn | 30 | 2017-06-08 |  |  | 3 |  | 47 | Shape Variation Tolerances | 6183
5401 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Allow definition of (validation) properties on dimensional_size and geometric_tolerance | 8 | 2017-06-08 |  |  | 5 |  | 41 | Fundamentals of product description and support | 5553
5685 | CRx PMI-2 | normal | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | EXPRESS layout of ENTITY characterized_item_within_representation does not follow SC4 directives | 2 | 2017-06-08 |  |  | In-work |  | 41 | Fundamentals of product description and support | 5553
5929 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Add Persistent ID capability to an aggregate of topological_representation_items | 12 | 2017-06-08 |  |  | 4 |  | 41 | Fundamentals of product description and support | 5553
6047 | CR_Geometry_2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Add FUNCTION get_representations_for_items to representation_schema | 8 | 2017-03-31 |  |  | In-work |  | 43 | Representation Structures | 5553
4658 | CRx PMI-2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | item_identified_representation_usage.wr1 | 16 | 2017-06-08 |  |  |  |  | 41 | Fundamentals of product description and support | 5553
5972 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | External Element References on Geometric Assembly | 12 | 2017-06-08 |  |  |  |  | 41 | Fundamentals of product description and support | 5553
6054 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | modification to product_property_representation_schema to support Bug 5972 | 8 | 2017-06-08 |  |  |  |  | 41 | Fundamentals of product description and support | 5553
6200 | CRx PMI-2 | normal | P2 | Internal | brandon.sapp@boeing.com | PDOCS | --- | Add a note to non_uniform_zone_definition in part 47 | 4 | 2017-06-08 |  |  |  |  | 47 | Shape Variation Tolerances | 6183
5496 | CRx PMI-2 | major technical | P2 | Internal | mikael.hedlind@scania.com | PDOCS | --- | New property_definition_denotation between a property to a dimension or tolerance | 0 | [5 empty] | 41 | Fundamentals of product description and support | 5553
6220 | CRx PMI-2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | PDOCS | ___ | ENTITY draughting_elements is too constraining for actual CAD practice | 2 | 2017-05-31 |  |  |  |  | 506 | Draughting elements | NA | 4251
5008 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | point_style: Make marker, marker_size and marker_colour OPTIONAL | 0
5029 | CR_Geometry_2 | minor technical | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | spelling errors in PART 46 EXPRESS SELECT types | 0
5503 | CR_Geometry_2 | normal | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | Add surface visual texture to Part 46 for tessellated geometry | 0
5817 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | Add colour on vertices to P46 for tessellated geometry | 0
5946 | CR_Geometry_2 | editorial | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | annotation_occurrence.WR2 EXPRESS text does not match English description | 0 | 2016-08-15
5967 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | P42 D.2 ExpG diagram's jump zone map incorrect | 0
5968 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | P42's Equations & Figures links corrections | 0
6040 | CR_Geometry_2 | normal | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | We need to update constraints on geometric_curve_set for bug 5006 | 0
6049 | CR_Geometry_2 | enhancement | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | Extend context_dependent_over_riding_styled_item in presentation_appearance_schema to support bug 5972 | 0
6050 | CR_Geometry_2 | minor technical | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | Redundant SELF.attribute_name in part 46 EXPRESS | 0
6137 | CR_Geometry_2 | minor technical | P4 | Internal | kevin.letutour@boost-conseil.com | PDOCS | --- | Clarify EXPRESS layout in representation_map.WR1 | 0
5901 | CR_Geometry_2 | enhancement | P4 | Internal | richard.s.zuray@boeing.com | PDOCS | --- | Add Persistent ID capability to topological items | 0
6048 | CR_Geometry_2 | enhancement | P4 | Internal | thomas.r.thurman@imonmail.com | PDOCS | --- | Add representation_reference to representation_schema to support bug 5972 | 0
4388 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | PDOCS | --- | Surface texture parameters, ISO 1302 | 226 |  |  |  |  | 2017-06-07 | 1110 | Surface Condition | NA
4781 | CR_PMI_3 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | CONFIRMED | --- | Complex symbols for "surface texture", "edges of undefined shape" and others
4835 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | IN_PROGRESS | --- | Geometric tolerances with unit sizes in degrees | 16 | 2017-05-19 |  |  |  |  | 47 | Shape Variation Tolerances | 6183
4836 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | FIXED | New Common Zone modifier CZ | 8 | ? |  |  |  |  | 47 | Shape Variation Tolerances | 6183
5402 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | PEXPRESS | --- | Definition of properties on Saved View, e.g. for default or active view | [5 empty] | 2017-06-02 | AP242 General |  | NA
6235 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | FIXED | PMI representation for "applies to all untoleranced surfaces" | [6 empty] | SMRL |  | NA
6236 | CRx PMI-2 | enhancement | P2 | Internal | claudia.c.huebner@boeing.com | CONFIRMED | --- | PMI representation for “unless otherwise specified" | [6 empty] | SMRL |  | NA
6232 | CRx PMI-2 | enhancement | P2 | Internal | claudia.c.huebner@boeing.com | New | --- | Missing UF modifier for "All over" and "All around" | [6 empty] | 1051 | Geometric Tolerance | 6201
6231 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | PEXPRESS | --- | ALL OVER in ISO TC213 | 16 | ? |  |  |  |  | 1051 | Geometric Tolerance | 6201
6257 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | PDOCS |  | characterized_item_within_representation.wr1 does not satisfy the requirement specified in the entity description. |  | 2017-06-08 |  |  |  |  | 41 | Fundamentals of product description and support | 5553
6252 | CRx PMI-2 |  | P2 |  | thomas.r.thurman@imonmail.com | PEXPRESS |  | Add draughting_model_item_association_with_placeholder | [6 empty] | 1311 | Associative Draughting elements | NA

## WG_#
Collector Bug | Bug Numbers | WG # |  |  |  | Schema Name
NA |  | N9532 | Claudia Huebner | CR-PMI Internal Review Checklist for 10303-506, 41, 43, 1362 | 2017-04-10
NA |  | N9533 | Claudia Huebner | CR-PMI Project Leader Checklist for 10303-506, 41, 43, 1362 | 2017-04-10
NA |  | N9534 | Claudia Huebner | CR-PMI Convener Checklist for 10303-506, 41, 43, 1362 | 2017-04-10
5553 | 4658, 5401, 5496,5685, 5902, 5929, 5972, 6054, 6257 | N9562 | Claudia Huebner | ISO 10303-41 ed5 Fundamentals of product description and support Document | 2017-04-20
|  | N9563 | Claudia Huebner | ISO 10303-41 ed5 Fundamentals of product description and support Concatenated EXPRESS | 2017-04-20
NA | 6047 | N9560 | Claudia Huebner | ISO 10303-43 ed5 Representation Structures Document | 2017-04-20
|  | N9561 | Claudia Huebner | ISO 10303-43 ed5 Representation Structures Concateneted EXPRESS | 2017-04-20
6183 | 4171, 4835, 4969, 6200 | N9665 |  | 10303-47 ed5 Shape variation tolerances Document | 2017-05-25
|  | N9666 |  | 10303-47 shape_dimension_schema EXPRESS v3 | 2017-05-25 | shape_dimension_schema
|  | N9667 |  | 10303-47 shape_tolerance_schema EXPRESS v3 | 2017-05-25 | shape_tolerance_schema
6041 | 6042 | N9660 |  | 10303-101 ed4 Draughting Document | 2017-05-25
|  | N9661 |  | 10303-101 ed4 Draughting EXPRESS | 2017-05-25 | draughting_element_schema
6044 | 5006 | N9668 |  | 10303-113 ed1 Mechanical design Document | 2017-05-25
|  | N9669 |  | 10303-113 mechanica_design_schema v1 | 2017-05-25 | mechanical_design schema
NA | 6220 | N9567 | Claudia Huebner | ISO 10303-506 ed4 Draughting elements Document | 2017-04-20
|  | N9568 | Claudia Huebner | ISO 10303-506 ed4 Draughting elements EXPRESS | 2017-04-20
NA | 6252 | N9662 |  | 10303-1311 ed5 nAssociative draughting element Document | 2017-05-25
|  | N9663 |  | 10303-1311 ed5 Associative draughting element ARM EXPRESS | 2017-05-25
|  | N9664 |  | 10303-1311 e3d5 Associative draughting element MIM EXPRESS | 2017-05-25
NA | 4251 | N9564 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts Documen | 2017-04-20
|  | N9565 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts EXPRESS ARM | 2017-04-20
|  | N9566 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts EXPRESS MIM | 2017-04-20
NA | 5142 | N9657 |  | 10303-1846 Mechanical-design | 2017-05-25
|  | N9658 |  | 10303-1846 Mechanical-design-ARM | 2017-05-25
|  | N9659 |  | 10303-1846 Mechanical-design-MIM | 2017-05-25
NA | 3675, 3789, 4171, 4836, 6231, 6232, 6235, 6236 | N9640 |  | White Paper on ‘All Around” and “all Over” | 2017-05-16
WG # not assgined yet for the following parts, etc.: 1032, 1051, 1110, 1814, All AP242 General, GD&T, SMRL

## Schedule
*
Blue Font | Assigned WG #
Black Font | No assigned WG #
Work Being Conducted from 5/5 - 6/9 |  |  |  | Grammar Review 5/24 - 7/3 |  |  | Internal Review Checklist from 6/6 - 7/21 |  |  | Project Lead Checklist 7/3 - 7/20 |  | Hand-off to Convener | Submit to IS ballot
Break-down of Work for Internal Review Checklist by Part* | Number of Bugs | Team Review | Date to complete bugs for part | Date to Hand-off to Darla | No. of hrs. for Grammar Review | Date to complete Grammar Review | Person | Estimated No. of HRS to conduct review | Date of Performance | Person | Date to do Checklist | 2017-07-21 | 2017-08-21
41 | 9 |  | 2017-06-22 |  | 4 |  | Rick | 6 | 2017-06-09
43 | 1 |  | 2017-06-05 |  | 1 |  | Tom | 3 | 2017-06-09
47 | 6 |  | 2017-06-09 |  | 4 |  | Rick | 6 | 2017-06-12
101 | 1 |  | 2017-06-30 |  | 2 |  | Brandon | 4 | 2017-06-09
113 | 1 |  | 2017-06-30 |  | 2 |  | Pierre | 3 | 2017-06-09
506 | 1 |  | 2017-06-30 |  | 1 |  | Tom | 3 | 2017-06-12
1032 | 1 |  | 2017-06-09 |  | 1 |  | Pierre | 3 | 2017-06-09
1051 | 5? |  |  |  | 2 |  | Rick | 5 | 2017-06-13
1110 | 1 |  |  |  | 1 |  | Pierre | 3 | 2017-06-12
1311 | 1
1362 | 1 |  |  |  | 1 |  | Rick | 3 | 2017-06-14
1814 | 1 |  |  |  | 1 |  | Brandon | 4 | 2017-06-13
1846 | 1 |  |  |  | 2
AP242 General | 1 |  |  |  | 1 |  | Pierre | 3 | 2017-06-12
GD&T | 3 |  |  |  | 2 |  | Rick | 4 | 2017-06-15
SMRL | 3 |  |  |  | 0 |  | Brandon | 8 | 2017-06-14
| 32 |  |  |  | 25 |  |  | 58

## Availability
Availability of Team Members: No. of hours per week
| March |  | April |  |  |  | May |  |  |  |  | June
| 20 - 24 | 27 - 31 | 3 - 7 | 10 - 14 | 17 - 21 | 24 - 28 | 1 - 5 | 8 - 12 | 15 - 19 | 22 - 26 | 29 - 2 | 5 - 9 | 12 - 16 | 19 - 23 | 26 - 30
Pierre Duchier | 0 | 0 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 0 | 6 | 4 | 4 | 0 | 0 | 50
Tom Hedberg | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 60
Claudia Huebner | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 90
Darla Nettles-Edwards | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 30
Brandon Sapp | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 224
Tom Thurman | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 156
Bryan Fischer | [15 empty] | 0
Rick Zuray |  |  | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 138
| 8 | 36 | 54 | 54 | 48 | 60 | 58 | 46 | 58 | 52 | 58 | 56 | 56 | 52 | 52 | 748
|  | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12 | 2017-05-19 | 2017-05-26 | 2017-06-02
Estimated Bug BurnDown |  | 42 | 37.3333 | 32.6667 | 28 | 23.3333 | 18.6667 | 14 | 9.3333 | 4.6667 | 0
Total Actual Bug Work Remaining |  | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
Actual Bug Burndown
Days not available (i.e. vacation, other company business, etc.)
Pierre Duchier
Tom Hedberg
Claudia Huebner
Darla Nettles-Edwards
Brandon Sapp
Tom Thurman
Bryan Fischer
Rick Zuray
|  |  | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12 | 2017-05-19 | 2017-05-26 | 2017-06-02
Total Estimated Time Remaining |  |  | 226 | 200.8889 | 175.7778 | 150.6667 | 125.5556 | 100.4444 | 75.3333 | 50.2222 | 25.1111 | 0
Total Actual Time Remaining |  |  | 2017-03-31: 226