## Remaining SOW
White paper for all over | White paper for counterbore, etc. | bug_id | target_milestone | bug_severity | priority | op_sys | assigned_to | bug_status | Status | short_desc | estimated_time | deadline |  | Review in PMI Mtg. | Granular Priortization | Ready for Team Review | Team Review | Internal Review CL | Grammar Review Hand-off | Part | Module | Collector Bugs feeding into 6033 | Blocking other bug
|  | 3551 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | Ready for IR | Diameter for Datum Target Point and - Line ? | 4 | 2017-05-12 | Complete |  |  | 2017-06-22 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | ??
x |  | 3675 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | Resolved | Ready for IR | Overriding geometric tolerances (ALL OVER, ALL AROUND, default) | ? | ? |  | x |  | 2017-06-20 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | ??
| x | 3701 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TCHecklist | Ready for IR review | spotface dimension discussion | 0 |  |  | x |  | 2017-07-18 | Done | 2017-07-21 | 2017-07-28 | 1846 | Mechanical design | 5142
| x | 3702 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TCHecklist | Ready for IR review | countersunk/counterbore/hole depth discussion | 0 | 2017-03-24 |  | x |  | 2017-07-18 | Done | 2017-07-21 | 2017-07-28 | GD&T |  | 6044
x |  | 3789 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | TREVIEW | Ready for IR | Globally-Applicable Specifications | ? | ? |  | x |  | 2017-06-20 | Done | 2017-07-21 | 2017-07-28 | GD&T |  | NA
|  | 3968 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | Ready for IR | How to relate datum/_system with TEDs? | 4 | 2017-03-31 |  |  |  |  | Done | 2017-07-21 | 2017-07-28 | GD&T |  | NA
x |  | 4171 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | Resolved | Ready for IR | ALL OVER in ISO TC213, unless otherwise specified geometric tolerance | 40 | ? |  |  |  | 2017-06-16 | Done | 2017-07-21 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 4251 | CRx PMI-2 | minor technical | P2 | Ballot Comment | brandon.sapp@boeing.com | TREVIEW | Ready for IR | AM 0442 Remove Global Rule RULE draughting_model_items_constraint | 4 | 2017-03-27 |  |  |  | 2017-06-20 | Done | 2017-07-21 | 2017-07-28 | 1362 | Dimension and tolerance callouts | 6045
|  | 4386 | CRx PMI-2 | general | P2 | Internal | richard.s.zuray@boeing.com | CONFIRMED | Ready for IR | Collector: Proposed Scope for Next PMI Work | 0 | [5 empty] | Done | 2017-07-21 | 2017-07-28 | AP242 general |  | NA
|  | 4388 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | PEXPRESS |  | Surface texture parameters, ISO 1302 | 0 |  |  |  |  | 2017-06-30 | PMI_3 | 2017-07-21 | 2017-07-28 | 1110 | Surface Condition | NA
|  | 4658 | CRx PMI-2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | item_identified_representation_usage.wr1 | 16 | 2017-06-08 |  |  |  | 2017-06-07 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 4835 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | PDOCS | ready for IR | Geometric tolerances with unit sizes in degrees | 16 | 2017-05-19 |  |  |  | 2017-06-16 | Done | 2017-07-21 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 4836 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | Ready for IR | New Common Zone modifier CZ | 8 | ? |  |  |  |  | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 4969 | CRx PMI-2 | normal | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | ISO 14660-1 withdrawn | 30 | 2017-06-08 |  |  | 3 | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 5006 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | PDOCS |  | New annotation_occurrence subtype to support "Minimal Presentation" for PMI | 8 | 2017-05-19 |  |  |  | 2017-06-27 | 2017-08-18 | 2017-07-21 | 2017-07-28 | 113 | Mechanical design application resource | 6044, 6041
|  | 5142 | CRx PMI-2 |  | P2 | Internal | brandon.sapp@boeing.com | PDOCS | In-work | new module--mechanical_design | [5 empty] | 2017-07-18 | 2017-08-18 | 2017-07-21 | 2017-07-28 | 1846 | Mechanical_Design | NA
|  | 5401 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | Allow definition of (validation) properties on dimensional_size and geometric_tolerance | 8 | 2017-06-08 |  |  | 5 | 2017-06-07 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5402 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | Definition of properties on Saved View, e.g. for default or active view | [5 empty] | 2017-07-18 | Done | 2017-07-21 | 2017-07-28 | 1315 |  | NA
|  | 5496 | CRx PMI-2 | major technical | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | Ready for IR | New property_definition_denotation between a property to a dimension or tolerance | 0 |  |  |  |  | 2017-06-07 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5553 | CRx PMI-2 | normal | P2 | Internal | richard.s.zuray@boeing.com | TREVIEW | Ready for IR | collector bug for part41 for CRx PMI2 | 0 | [5 empty] | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5685 | CRx PMI-2 | normal | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | EXPRESS layout of ENTITY characterized_item_within_representation does not follow SC4 directives | 2 | 2017-06-08 |  |  | In-work | 2017-06-07 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5902 | CRx PMI-2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | IIRU and GISU uniqueness rules | 0 | 2017-05-05 |  |  |  | 2017-06-15 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5915 | CRx PMI-2 | normal | P2 | Internal | pierre.duchier@airbus.com | TREVIEW | Ready for IR | Non uniform tolerance zone inconsistency | 8 | 2017-06-08 |  |  |  | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 5929 | CR_Geometry_2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | Add Persistent ID capability to an aggregate of topological_representation_items | 12 | 2017-06-08 |  |  | 4 | 2017-06-19 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 5972 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | External Element References on Geometric Assembly | 12 | 2017-06-08 |  |  |  | 2017-06-07 | Done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 6041 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | IN_PROGRESS | Ready for IR | Collector bug for P101 for CRx PMI 2 | 0 | [5 empty] | Done | 2017-07-06 | 2017-07-28 | 101 | Draughting | 6041
|  | 6042 | CRx PMI-2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | change draughting_callout_element to extensible generic_entity SELECT to allow extension in part 113 for bug 5006. | 12 | 2017-05-05 |  |  |  | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 101 | Draughting | 6041
| x | 6044 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | PDOCS | Ready for IR | Collector bug for part 113 | 0 | [5 empty] | 2017-08-18 | 2017-07-21 | 2017-07-28 | 113 | Mechnical design application resource | 6044
|  | 6045 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | CONFIRMED | Ready for IR | Collector bug for AM 1362 Dimension and tolerance callouts for bug 5006 | 0 | [5 empty] | Done | 2017-06-28 | 2017-07-28 | 1362 | Dimension and tolerance callouts | 6045
|  | 6047 | CR_Geometry_2 | enhancement | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | Add FUNCTION get_representations_for_items to representation_schema | 8 | 2017-03-31 |  |  | In-work | 2017-06-14 | done | 2017-06-28 | 2017-07-07 | 43 | Representation Structures | 5553
|  | 6048 | CR_Geometry_2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | Add representation_reference to representation_schema to support bug 5972 | 0 |  |  |  |  | 2017-06-14 | done | 2017-06-28 | 2017-07-07 | 43
|  | 6054 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | Resolved / duplicate | Ready for IR | modification to product_property_representation_schema to support Bug 5972 | 8 | 2017-06-08 |  |  |  | 2017-06-07 | done | 2017-06-28 | 2017-07-07 | 41 | Fundamentals of product description and support | 5553
|  | 6137 | CR_Geometry_2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | PDOCS | Ready for IR | Clarify EXPRESS layout in representation_map.WR1 | 0 |  |  |  |  | ?? | done | 2017-06-28 | 2017-07-07 | 43 | Registration structures
|  | 6141 | CRx PMI-2 | normal | P1 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | AM 1032 Shape_property_assignment Remove geometric_item_specific_usage.ur1 to support bug #5902 | 0 | 2017-05-19 |  |  |  | 2017-06-14 | Done | 2017-07-06 | 2017-07-28 | 1032 | Shape Property Assignment | NA
| x | 6183 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | IN_PROGRESS | Ready for IR | Collector bug for Part 47 for CRx PMI-2 | 0 | [5 empty] | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 6200 | CRx PMI-2 | normal | P2 | Internal | pierre.duchier@airbus.com | TREVIEW | Ready for IR | Add a note to non_uniform_zone_definition in part 47 | 4 | 2017-06-08 |  |  |  | 2017-06-20 | done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 6201 | CRx PMI-2 | enhancement | P2 | Internal | richard.s.zuray@boeing.com | CONFIRMED | Ready for IR | Collector bug for AM 1051 Geometric_tolerance for CRx_PMI 2 | 0 | [5 empty] | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | 6201
|  | 6202 | CRx PMI-2 | normal | P2 | Internal | pierre.duchier@airbus.com | TREVIEW | Ready for IR | Add Non uniform tolerance zone rule to AM Geometric_tolerance | 4 | 2017-05-26 |  |  |  | 2017-06-27 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | 6201
| x | 6208 | CRx PMI-2 | enhancement | P1 | Internal | thomas.r.thurman@imonmail.com | PDOCS |  | Collector: New AM Mechanical_design | 40 | 2017-04-28 |  |  |  |  | 2017-08-18 | 2017-07-21 | 2017-07-28 | 1846 | Mechanical_Design | NA
|  | 6220 | CRx PMI-2 | minor technical | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | ENTITY draughting_elements is too constraining for actual CAD practice | 2 | 2017-05-31 |  |  |  | 2017-06-20 | Done | 2017-06-28 | 2017-07-07 | 506 | Draughting elements | NA | 4251
x |  | 6231 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | TREVIEW | Ready for IR | ALL OVER in ISO TC213 | 16 | ? |  |  |  | 2017-06-22 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | 6201
x |  | 6232 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | Resolved | Ready for IR | Missing UF modifier for "All over" and "All around" | [5 empty] | 2017-06-22 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance | 6201
x |  | 6235 | CRx PMI-2 | enhancement | P2 | Internal | Keith.Hunten@gmail.com | RESOLVED | Ready for IR | PMI representation for "applies to all untoleranced surfaces" | [6 empty] | Done | 2017-07-06 | 2017-07-28 | SMRL |  | NA
|  | 6235 | CRx PMI-2 | enhancement | P1 |  | Keith.Hunten@gmail.com | Resolved / duplicate | Ready for IR | PMI representation for "applies to all untoleranced surfaces" | [6 empty] | Done |  |  | SMRL
x |  | 6236 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | TREVIEW | Ready for IR | PMI representation for “unless otherwise specified" | [5 empty] | 2017-06-20 | Done | 2017-07-21 | 2017-07-28 | SMRL |  | NA
|  | 6250 | CRx PMI-2 | enhancement | P1 |  | mike.ward@eurostep.com | CONFIRMED |  | Redundant EXPRESS ascii file is included in SMRL | [6 empty] | Before SMRL build
|  | 6252 | CRx PMI-2 |  | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | Add draughting_model_item_association_with_placeholder | [5 empty] | 2017-06-27 | Done | 2017-07-21 | 2017-07-28 | 1311 | Associative Draughting elements | NA
|  | 6274 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR | Collector bug for 520::minor re-arrangement of EXPRESS needed to support bug 5006 | [5 empty] | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 520 | Associative Draughting elements | NA
x |  | 6278 | CRx PMI-2 |  | P2 |  | Keith.Hunten@gmail.com | Resolved | Ready for IR | Missing UF modifier for "All over" and "All around" | [5 empty] | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances | 6183
|  | 6279 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | MIM does not match ARM in datc_draughting_model_item_definition | [5 empty] | ?? | Done | 2017-06-28 | 2017-07-28 | 1362 | Dimension and tolerance callouts
x |  | 6284 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | RESOLVED | Ready for IR | ALL AROUND geometric tolerance in AM 1051 | [5 empty] | 2017-06-20 | Done | 2017-07-21 | 2017-07-28 | 1051 | Geometric Tolerance
x |  | 6285 | CRx PMI-2 | enhancement | P2 | Internal | thomas.r.thurman@imonmail.com | RESOLVED | Ready for IR | ALL AROUND geometric tolerance in p47 | [5 empty] | 2017-06-20 | Done | 2017-07-06 | 2017-07-28 | 47 | Shape Variation Tolerances
|  | 6295 | CRx PMI-2 | enhancement | P2 | Internal | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | Add Draughting_model_item_association_with_placeholder | [5 empty] | ?? | Done | 2017-06-28 | 2017-07-28 | 1362 | Dimension and tolerance callouts
|  | 6298 | CRx PMI-2 | enhancement | P2 |  | pierre.duchier@airbus.com | Resolved / duplicate | Ready for IR | Geometric tolerances with unit sizes in degrees | [6 empty] | Done |  | 2017-07-28 | 1051
|  | 6299 | CRx PMI-2 | enhancement | P2 | Internal | pierre.duchier@airbus.com | PEXPRESS | Ready for IR review | Geometric tolerances with unit sizes in degrees | [6 empty] | Done | 2017-07-21 | 2017-07-28 | 1051
|  | 6302 | CRx PMI-2 | enhancement | P1 |  | thomas.r.thurman@imonmail.com | Resolved | Ready for IR review | update AM 442 references to support new annotation_occurrence subtype for bug 5006 | [6 empty] | Done |  |  | 442 | AP242 managed model based 3D engineering
|  | 6307 | CRx PMI-2 | enhancement | P1 |  | mike.ward@eurostep.com | CONFIRMED |  | IR CR build output sys directory includes html files for schemas that are not specified in the publication index. | [6 empty] | Before SMRL build
|  | 6313 | CRx PMI-2 | enhancement | P1 |  | pierre.duchier@airbus.com | PDOCS | Ready for IR review | remove feature_occurrence from shape_aspect_definition_schema.exp | [6 empty] | Done |  |  | 47 | shape variation tolerances
|  | 6314 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | TREVIEW | Ready for IR | add postive_length_measure_with_unit and positive_plane_angle_measure_with_unit to measure schema | [6 empty] | Done |  |  | 41 | Fundamentals of product description and support
| x | 6315 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | PDOCS |  | countersink/counterbore/hole implementation in AM 1846 | [6 empty] | 2017-08-18 |  |  | 1846 | Mechanical design
| x | 6316 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | AM 1054 "collector bug" :: add positive_plane_angle_measure | [6 empty] | Done |  |  | 1054 | Value with unit
| x | 6317 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | TREVIEW | Ready for IR review | AM 1753 "collector bug" :: add Positive_angle_data_element Positive_length_data_element | [6 empty] | Done |  |  | 1753 | Value with unit extension
| x | 6318 | CRx PMI-2 | enhancement | P1 |  | pierre.duchier@airbus.com | TREVIEW | Ready for IR | Add length_tolerance_value and plane_angle_tolerance_value to shape_tolerance_schema | [6 empty] | Done |  |  | 47 | Shape Variation Tolerances
| x | 6320 | CRx PMI-2 | enhancement | P1 |  | pierre.duchier@airbus.com | PDOCS | Ready for IR | Collector bug for AM 1050 dimension_tolerance and add subtypes of Plus_minus_bound | [6 empty] | Done |  |  | 1050 | Dimension_Tolerance
| x | 6321 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | TCHecklist | Ready for IR review | Add USE FROM AM Mechanical_design to AM 0442 | [6 empty] | Done |  |  | 442 | AP242 managed model based 3D engineering
|  | 6331 | Near term | enhancement | P2 |  | mike.ward@eurostep.com | CONFIRMED |  | The 'move-to-resource' attribute in resource.xml is not rendered in html | [6 empty] | ??
|  | 6327 | CRx PMI-2 | enhancement | P1 |  | thomas.r.thurman@imonmail.com | Resolved | Ready for IR review | Publication Index: Can't add wg numbers for Longform ARM and Longform MIM | [6 empty] | Done
|  | 6333 | 242-2-DIS | enhancement | P2 |  | thomas.r.thurman@imonmail.com | PEXPRESS | [8 empty] | 2017-08-03 |  |  | 45 | material and other engineering materials
|  | 6326 | CRx PMI-2 | enhancement | P1 |  | pierre.duchier@airbus.com | TREVIEW | Ready for IR review | Missing entities in the USE FROM shape_tolerance_schema and shape_aspect_definition_schema | [6 empty] | Done |  |  | 1051 | Geometric Tolerance
|  | 6337 | CRx PMI-2 | enhancement | P1 |  | brandon.sapp@boeing.com | PDOCS |  | Add counterbore_countersink_schema to part 113 | [6 empty] | 2017-08-18 |  |  | 113

## WG_#
Collector Bug | Bug Numbers | WG # |  |  | Date | Schema Name
NA | NA | N9532 | Claudia Huebner | CR-PMI Internal Review Checklist for 10303-506, 41 | 2017-04-10 |  | Order of checklists (ready to go)
NA |  | N9533 | Claudia Huebner | CR-PMI Project Leader Checklist for 10303-506, 41 | 2017-04-10 |  |  | IR | Project Lead
NA |  | N9534 | Claudia Huebner | CR-PMI Convener Checklist for 10303-506, 41 | 2017-04-10 |  | 506 | completed | in work
NA |  | N9712 |  | CR-PMI Internal Review Checklist for 442, 1032, 1050, 1051, 1054, 1110, 1311, 1315, 1362, 1753 | 2017-07-18 |  | 101
NA |  | N9713 |  | CR-PMI Project Leader Checklist for 10303-442, 1032, 1050, 1051, 1054, 1110, 1311, 1315, 1362, 1753 | 2017-07-18 |  | 520
NA |  | N9714 |  | CR-PMI Convener Checklist for 10303-442, 1032, 1050, 1051, 1054, 1110, 1311, 1315, 1362, 1753 | 2017-07-18 |  | 47 (hold up resolving of bug 4835)
5553 | 4658, 5401, 5496,5685, 5902, 5929, 5972, 6054, 6257 | N9562 | Claudia Huebner | ISO 10303-41 ed5 Fundamentals of product description and support Document | 2017-04-20 |  | 442, 1032, 1050, 1051, 1054, 1110, 1311, 1315, 1362, 1753
|  | N9684 | Claudia Huebner | ISO 10303-41 ed8 product_property_definition_schema.exp EXPRESS | 2017-06-08 | product_property_definition_schema.exp | 113
|  | N9685 |  | ISO 10303-41 ed8 product_property_representation_schema EXPRESS | 2017-06-08 | product_property_representation_schema | 1846
|  | N9686 |  | ISO 10303-41 ed8 basic_attribute_schema EXPRESS | 2017-06-08 | basic_attribute_schema
|  | N9715 |  | 10303-41 ed5 measure_schema EXPRESS | 2017-07-21
6183 | 4171, 4835, 4969, 6200 | N9776 |  | CR-PMI Internal Review Checklist for 10303-47 | 2017-08-09
|  | N9777 |  | CR-PMI Project Leader Checklist for 10303-47 | 2017-08-09
|  | N9778 |  | CR-PMI Convener Checklist for 10303-47 | 2017-08-09
|  | N9665 |  | 10303-47 ed5 Shape variation tolerances Document | 2017-08-09
|  | N9666 |  | 10303-47 shape_dimension_schema EXPRESS v3 | 2017-08-09 | shape_dimension_schema
|  | N9667 |  | 10303-47 shape_tolerance_schema EXPRESS v3 | 2017-08-09 | shape_tolerance_schema
6041 | 6041 | N9779 |  | CR-PMI Internal Review Checklist for 10303-101 | 2017-08-09
|  | N9780 |  | CR-PMI Project Leader Checklist for 10303-101 | 2017-08-09
|  | N9781 |  | CR-PMI Convener Checklist for 10303-101 | 2017-08-09
|  | N9660 |  | 10303-101 ed4 Draughting Document | 2017-08-09
|  | N9661 |  | 10303-101 ed4 Draughting EXPRESS | 2017-08-09 | draughting_element_schema
6044 | 5006, 6337 | N9782 |  | CR-PMI Internal Review Checklist for 10303-113 | 2017-08-09
|  | N9783 |  | CR-PMI Project Leader Checklist for 10303-113 | 2017-08-09
|  | N9784 |  | CR-PMI Convener Checklist for 10303-113 | 2017-08-09
|  | N9785 |  | 10303-113 ed1 Mechanical design Document | 2017-08-09
|  | N9786 |  | 10303-113 mechanica_design_schema v1 | 2017-08-09 | mechanical_design schema
|  | N9785 |  | 10303-113 counterbore_countersink_schema v1 | 2017-08-09
| 6321 | N9716 |  | 10303-442 ed3 AP242 managed model based 3D engineering Document | 2017-08-09
|  | N9717 |  | 10303-442 ed3 AP242 managed model based 3D engineering ARM EXPRESS | 2017-08-09
|  | N9718 |  | 10303-442 ed3 AP242 managed model based 3D engineering MIM EXPRESS | 2017-08-09
|  | N9719 |  | 10303-442 ed3 AP242 managed model based 3D engineering ARM longform | 2017-08-09
|  | N9720 |  | 10303-442 ed3 AP242 managed model based 3D engineering MIM Longform | 2017-08-09
NA | 6220 | N9567 | Claudia Huebner | ISO 10303-506 ed4 Draughting elements Document | 2017-08-09
|  | N9568 | Claudia Huebner | ISO 10303-506 ed4 Draughting elements EXPRESS | 2017-08-09
NA | 6274 | N9786 |  | CR-PMI Internal Review Checklist for 10303-520 | 2017-08-09
|  | N9787 |  | CR-PMI Project Leader Checklist for 10303-520 | 2017-08-09
|  | N9788 |  | CR-PMI Convener Checklist for 10303-520 | 2017-08-09
|  | N9670 |  | 10303-520 ed 3 Associative draughting elements Document | 2017-08-09
|  | N9671 |  | 10303-520 aic_associative_draughting_elements schema v3 | 2017-08-09
NA | 6141 | N9672 |  | 10303-1032 ed8 Shape Property Assignment Document | 2017-08-09
|  | N9673 |  | 10303-1032 ed8 Shape Property Assignment ARM EXPRESS | 2017-08-09
|  | N9674 |  | 10303-1032 ed8 Shape Property Assignment MIM EXPRESS | 2017-08-09
| 6320 | N9721 |  | 10303-1050 ed8 Dimension Tolerance Document | 2017-08-09
|  | N9722 |  | 10303-1050 ed8 Dimension Tolerance ARM EXPRESS | 2017-08-09
|  | N9723 |  | 10303-1050 ed8 Dimension Tolerance MIM EXPRESS | 2017-08-09
6201 | 3551, 3675, 6202, 6231, 6232 | N9675 |  | 10303-1051 ed8 Geometric Tolerance Document | 2017-08-09
|  | N9676 |  | 10303-1051 ed8 Geometric Tolerance ARM EXPRESS | 2017-08-09
|  | N9677 |  | 10303-1051 ed8 Geometric Tolerance MIM EXPRESS | 2017-08-09
| 6316 | N9724 |  | 10303-1054 ed4 Value with unit Document | 2017-08-09
|  | N9725 |  | 10303-1054 ed4 Value with unit ARM Express | 2017-08-09
|  | N9726 |  | 10303-1054 ed4 Value with unit MIM Express | 2017-08-09
NA | 4388 | N9678 |  | 10303-1110 ed6 Surface Condition Document | 2017-08-09
|  | N9679 |  | 10303-1110 ed6 Surface Condition ARM EXPRESS | 2017-08-09
|  | N9680 |  | 10303-1110 ed6 Surface Condition MIM EXPRESS | 2017-08-09
NA | 6252 | N9662 |  | 10303-1311 ed5 nAssociative draughting element Document | 2017-08-09
|  | N9663 |  | 10303-1311 ed5 Associative draughting element ARM EXPRESS | 2017-08-09
|  | N9664 |  | 10303-1311 e3d5 Associative draughting element MIM EXPRESS | 2017-08-09
NA | 5402 | N9709 |  | 10303-1315 ed3 Mechanical design presentation representation with draughting Document | 2017-08-09
|  | N9710 |  | 10303-1315 ed3 Mechanical design presentation representation with draughting ARM EXPRESS | 2017-08-09
|  | N9711 |  | 10303-1315 ed3 Mechanical design presentation representation with draughting MIM EXPRESS | 2017-08-09
6045 | 4251, 6279, 6295 | N9564 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts Documen | 2017-08-09
|  | N9565 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts EXPRESS ARM | 2017-08-09
|  | N9566 | Claudia Huebner | ISO 10303-1362 ed4 Dimension and tolerance callouts EXPRESS MIM | 2017-08-09
| 6317 | N9727 |  | 10303-1753 ed5 Value with unit extention Document | 2017-08-09
|  | N9728 |  | 10303-1753 ed5 Value with unit extention ARM EXPRESS | 2017-08-09
|  | N9729 |  | 10303-1753 ed5 Value with unit MIM EXPRESS | 2017-08-09
6208 | 3701, 5142 | N9789 |  | CR-PMI Internal Review Checklist for 10303-1846 | 2017-08-09
|  | N9790 |  | CR-PMI Project Leader Checklist for 10303-1846 | 2017-08-09
|  | N9791 |  | CR-PMI Convener Checklist for 10303-1846 | 2017-08-09
|  | N9657 |  | 10303-1846 e1 Mechanical-design Document | 2017-05-25
|  | N9658 |  | 10303-1846 Mechanical-design-ARM | 2017-05-25
|  | N9659 |  | 10303-1846 Mechanical-design-MIM | 2017-05-25
NA | 3675, 3789, 4171, 4836, 6231, 6232, 6235, 6236 | N9640 |  | White Paper on ‘All Around” and “all Over” | 2017-05-16

## Schedule
Legend
| Blue Font | Assigned WG #
| Black Font | No assigned WG #
Bug Distribution (by part/module, etc // Batch Number 1, 2, 3) |  |  |  | Internal Review Checklist |  |  | Project Lead Checklist |  | English Quality Review: 1. 7/7 - 7/20 2. 7/21 - 8/4 |  |  | Hand-off to Convener | Submit to IS ballot
Batch No. | Break-down of Work for Internal Review Checklist by Part / Module* | Number of Bugs | Team Review | Person | Estimated No. of HRS to conduct review | Date of Performance | Person | Date to do Checklist | Date to Hand-off to Darla | No. of hrs. for Grammar Review | Date to complete Grammar Review | 2017-08-04 | 2017-08-21
1 | 41 | 9 | 2017-06-15 | Rick | 6 | 2017-06-28 | Tom / Claudia | 2017-07-06 | 2017-07-07 | 4 | 2017-07-21
2 | 47 | 9 | 2017-06-20 | Rick | 6 | 2017-07-06 | Tom / Claudia | 2017-07-10 | 2017-07-14 | 4 | 2017-07-28
2 | 101 | 2 |  | Rick | 4 | 2017-07-06 | Tom / Claudia | 2017-07-10 | 2017-07-14 | 2 | 2017-07-28
2 | 113 | 2 |  | Rick | 3 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 2 | 2017-08-04
442
1 | 506 | 1 | 2017-06-20 | Rick | 3 | 2017-06-28 | Tom / Claudia | 2017-07-06 | 2017-07-07 | 1 | 2017-07-21
2 | 520 | 1 |  | Rick | 2 | 2017-07-06 | Tom / Claudia | 2017-07-10 | 2017-07-14 | 1 | 2017-07-28
2 | 1032 | 1 |  | Rick | 3 | 2017-07-06 | Tom / Claudia | 2017-07-10 | 2017-07-14 | 1 | 2017-07-28
1050
2 | 1051 | 9 |  | Rick | 5 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 2 | 2017-08-04
1054
2 | 1110 | 1 |  | Rick | 3 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 1 | 2017-08-04
2 | 1311 | 1 |  | Rick | 2 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 1 | 2017-08-04
2 | 1315 | 1 |  | Rick |  | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 0.5 | 2017-08-04
2 | 1362 | 4 | 2017-06-20 | Rick | 3 | 2017-06-28 | Tom / Claudia | 2017-07-06 | 2017-07-07 | 1 | 2017-07-21
1753
2 | 1846 | 3 |  | Rick | 3 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 2 | 2017-08-04
2 | AP242 General | 1 |  | Rick | 3 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 0.5 | 2017-08-04
2 | GD&T | 3 |  | Rick | 4 | 2017-07-21 | Tom / Claudia | 2017-07-26 | 2017-07-28 | 2 | 2017-08-04
2 | SMRL | 2 |  | Rick | 8 | 2017-07-21 | Tom / Claudia | 2017-07-10 | 2017-07-28 | 0 | 2017-08-04
| Total No. of bugs | 50 |  |  | 58 |  |  |  |  | 25

## Availability
Availability of Team Members: No. of hours per week
| March |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September
| 20 - 24 | 27 - 31 | 3 - 7 | 10 - 14 | 17 - 21 | 24 - 28 | 1 - 5 | 8 - 12 | 15 - 19 | 22 - 26 | 29 - 2 | 5 - 9 | 12 - 16 | 19 - 23 | 26 - 30 | 3 - 7 | 10 - 14 | 17 -21 | 24 - 28 | 1 - 4 | 7 - 11 | 14 - 18 | 21 - 25 | 28 - 31 | 4 - 8 | 11 -15 | 18 - 22 | 25 - 29
Pierre Duchier | 0 | 0 | 6 | 6 | 0 | 6 | 6 | 6 | 6 | 0 | 6 | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 4 | 0 | 4 | 4 | 4 | 10 | 4 | 4 | 66
Tom Hedberg | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | MSEC in LA | 4 | 4 | 4 | Vacation | 2 | 4 | 4 | 4 | 4 | 4 | 4 | MTConnect TAG | 2 | 20 | GPDIS | 4 | 64
Claudia Huebner | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 8 | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 8 | Vacation | Vacation | 110
Darla Nettles-Edwards | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 47
Brandon Sapp | March 20 - 24: 0; March 27 - 31: 16; April 3 - 7: 16; April 10 - 14: 16; April 17 - 21: 16; April 24 - 28: 16; May 1 - 5: 16; May 8 - 12: 16; May 15 - 19: 16; May 22 - 26: 16; May 29 - 2: 16; June 5 - 9: 16; June 12 - 16: 16; June 19 - 23: 16; June 26 - 30: 40; July 3 - 7: 0 | 88
Tom Thurman | March 20 - 24: 0; March 27 - 31: 12; April 3 - 7: 12; April 10 - 14: 12; April 17 - 21: 12; April 24 - 28: 12; May 1 - 5: 12; May 8 - 12: 0; May 15 - 19: 12; May 22 - 26: 12; May 29 - 2: 12; June 5 - 9: 12; June 12 - 16: 12; June 19 - 23: 12; June 26 - 30: 12 | 48
Rick Zuray | June 5 - 9: 10; June 12 - 16: 10; June 19 - 23: 10; June 26 - 30: 10; July 3 - 7: 4; July 10 - 14: 8; July 17 -21: 8; July 24 - 28: 8; August 1 - 4: 8; August 7 - 11: Vacation; August 14 - 18: Vacation; August 21 - 25: 8; August 28 - 31: 8; September 4 - 8: 8; September 11 -15: 8; September 18 - 22: 8 | 116
|  |  | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 10 | 50 | 54 | 50 | 72 | 15 | 23 | 31 | 31 | 31 | 19 | 15 | 27 | 23 |  |  |  |  | 539
| 8 | 36 | 54 | 54 | 48 | 60 | 58 | 46 | 58 | 52 | 58
Days not available (i.e. vacation, other company business, etc.)
Pierre Duchier
Tom Hedberg
Claudia Huebner
Darla Nettles-Edwards
Brandon Sapp
Tom Thurman |  |  | 2017-03-31 | 2017-04-07 | 2017-04-14 | 2017-04-21 | 2017-04-28 | 2017-05-05 | 2017-05-12 | 2017-05-19 | 2017-05-26
Bryan Fischer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rick Zuray |  |  | 2017-03-31: 0
2017-06-02
Total Estimated Time Remaining | [11 empty] | #REF!
Total Actual Time Remaining