## Master CRs listing
Part number | Module or IR name | Part Edition in CR | Final Listing | STEPmod publication index | Status | Comment | Listing and STEPmod indexes aligment check | publication_index_CR11 | stepmod tag CR11 | Howard Mason listing | Tom Bluhm listing | Lothar Klein listing | Existing CR ? | to add For SMRL V8.7 | Existing CR after work? | fully aligned
1001 | Appearance assignment | 7 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry_2 |  | CR_Geometry_2 | 1 |  | 1 | 0
1004 | elemental_geometric_shape | 9 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1005 | elemental_topology | 5 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1012 | approval | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1019 | product_view_definition | 3 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1023 | part_view_definition | 3 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1026 | assembly_structure | 5 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1027 | contextual_shape_positioning | 7 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1032 | shape_property_assignment | 7 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1041 | product_view_definition_relationship | 3 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1042 | work_request | 3 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1050 | dimension_tolerance | 6 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1051 | geometric_tolerance | 7 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1054 | value_with_unit | 3 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_EWH | CR_Geometry | 1 |  | 1 | 0.5
1063 | product_occurrence | 4 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1063 | product_occurrence | 5 | CR_EWH | CR_EWH | In work |  | 1
1064 | event | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1103 | product_class | 5 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1108 | specification_based_configuration | 3 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1110 | surface_conditions | 5 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_Geometry/CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 0.5
1111 | classification_with_attributes | 5 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1118 | measure_representation | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1122 | document_assignment | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1130 | derived_shape_element | 5 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1131 | construction_geometry | 5 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1131 | construction_geometry | 6 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry_2 |  | CR_Geometry_2 | 1 |  | 1 | 0
1147 | manufacturing_configuration_effectivity | 3 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1231 | product_data_management | 5 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1232 | design_material_aspects | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1248 | product_breakdown | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1309 | drawing_definition | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1311 | associative_draughting_elements | 4 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1312 | draughting_element_specialisations | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1318 | procedural_solid_model | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1319 | solid_with_local_modification | 3 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1323 | basic_geometric_topology | 4 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1343 | product_placement | 5 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1346 | numeric_function | 4 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_PDM_1 | CR_composites | 1 |  | 1 | 0.5
1349 | incomplete_data_reference_mechanism | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1350 | inertia_characteristics | 3 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1311 | associative_draughting_elements | 5 | CR_PMI_2 | CR_PMI_2 | In work |  | 1
1362 | dimension_and_tolerance_callouts | 3 |  |  | In work |  | 1 |  |  | CR_PM2
113 | mechanical_design | 1 |  |  | In work |  | 1
new module | mechanical_design | 1 |  |  | In work |  | 1
506 | associative_draughting_elements | 3 |  |  | In work | schema : mechanical_design | 1
101 | draughting | 4 |  |  | In work | schema : draughting_element_schema, aic_draughting_elements | 1
1380 | fea_definition_relationships | 2 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_209 | CR_composites | 1 |  | 1 | 0.5
1386 | mesh_topology | 2 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_Geometry | CR_composites | 1 |  | 1 | 0.5
1399 | property_as_definition | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1404 | geometric_model_2d_3d_relationship | 2 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1507 | geometrically_bounded_surface | 3 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 |  | CR_Geometry | CR_Geometry | 1 |  | 1 | 0
1509 | manifold_surface | 5 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1514 | advanced_boundary_representation | 4 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1520 | product_data_quality_definition | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_PDM_1 ? | CR_Geometry | CR_PDM ? | 1 |  | 1 | #REF!
1521 | product_data_quality_criteria | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1522 | product_data_quality_inspection_result | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1523 | shape_data_quality_criteria | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1524 | shape_data_quality_inspection_result | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1525 | composite_surface | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1526 | numeric_expression | 2 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_PDM_1 | CR_composites | 1 |  | 1 | 0.5
1527 | elementary_function | 2 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_PDM_1 | CR_composites | 1 |  | 1 | 0.5
1601 | altered_package | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1602 | altered_part | n/a | none | none | Not changed | No changes | 1 |  | CR11 |  |  |  | 1 |  | 1 | 0
1628 | design_product_data_management | 6 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1634 | assembly_component_placement_requirements | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1635 | assembly_functional_interface_requirement | 3 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1636 | assembly_module_design | 5 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1638 | assembly_module_with_cable_component_2d | n/a | none | none | Not changed | Bug 6243: No changes, reverted to SMRLv6, cancel N number : action KLT | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1639 | assembly_module_with_cable_component_3d | n/a | none | none | Not changed | Bug 6243: No changes, reverted to SMRLv6, cancel N number : action KLT | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1640 | assembly_module_with_macro_component | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1641 | assembly_module_with_subassembly | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1642 | assembly_module_usage_view | 5 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1643 | assembly_module_with_interconnect_component | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1644 | assembly_module_with_cable_component | 4 | CR_210_1 | CR_210_1 | Publication index ready | Bug 6243 | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1645 | assembly_module_with_packaged_connector_component | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1646 | footprint_definition | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1648 | assembly_physical_requirement_allocation | 4 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1649 | assembly_technology | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1650 | bare_die | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1652 | basic_geometry | 6 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1653 | cable | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 0
1654 | characteristic | 6 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1656 | component_grouping | 5 | CR_210_1 | CR_210_1 | Publication index ready | Bug 6243 | 1 | Yes | CR11 | CR_210_1 | CR_EWH | CR_210_1 | 1 |  | 1 | 0.5
1657 | component_feature | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1660 | datum_difference_based_model | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1662 | design_specific_assignment_to_assembly_usage_view | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 |  | CR_210_2 | 1 |  | 1 | 0.5
1666 | extended_geometric_tolerance | withdrawn | CR_itemshape_1 | CR_itemshape_1 | Balloted | withdrawn | 1 | Yes | CR11 |  | CR_PDM_1 | CR_itemshape_1 | 1 |  | 1 | 0
1668 | fabrication_joint | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1670 | fabrication_technology | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1671 | feature_and_connection_zone | 5 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1674 | functional_assignment_to_part | 3 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1676 | Functional_decomposition_to_design | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 |  |  | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1679 | functional_specification | 3 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1681 | generic_material_aspects | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1682 | interconnect_2d_shape | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1685 | interconnect_module_to_assembly_module_relationship | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1686 | interconnect_module_usage_view | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1687 | interconnect_module_with_macros | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1689 | interconnect_physical_requirement_allocation | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1690 | interconnect_placement_requirements | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1691 | interface_component | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1692 | land | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1696 | layered_interconnect_module_3d_design | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1698 | layered_interconnect_module_design | 6 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1700 | layered_interconnect_module_with_printed_component_design | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1701 | layout_macro_definition | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1702 | manifold_subsurface | 4 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1703 | model_parameter | 5 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1704 | network_functional_design_view | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1705 | functional_usage_view | 5 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1706 | non_feature_shape_element | 5 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1707 | package | 6 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1708 | packaged_connector_model | 3 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1709 | packaged_part_white_box_model | n/a | none | none | Not changed | Bug 5881: No changes, reverted to SMRLv6, cancel N number : action KLT | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1710 | packaged_part_black_box_model | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1711 | part_external_reference | 4 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1712 | part_feature_function | 4 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1714 | part_feature_location | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1716 | layered_interconnect_complex_template | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1717 | Part template 3d shape | 4 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 |  |  | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 0
1718 | layered_interconnect_simple_template | 6 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1721 | physical_component_feature | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1722 | part_template | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_itemshape_2 | CR_210_2 | 1 |  | 1 | 0.5
1723 | physical_node_requirement_to_implementing_component_allocation | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1724 | physical_unit_2d_design_view | 5 | CR_210_2 | CR_210_2 | Publication index ready |  | 1
1725 | Physical_unit_3D_design_view | 5 | CR_210_2 | CR_210_2 | Publication index ready | change N number desc. : ed5 not 4: KLT action | 1 |  |  | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1726 | physical_unit_2d_shape | 4 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1727 | physical_unit_3d_shape | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 |  | CR_210_2 | 1 |  | 1 | 0.5
1728 | physical_unit_design_view | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1729 | Physical unit interconnect definition | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 |  |  | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
1731 | constructive_solid_geometry_2d | 5 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1731 | constructive_solid_geometry_2d | 6 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1
1732 | Physical unit usage view | 5 | CR_EWH | CR_EWH | In work |  | 1 |  |  | CR_EWH |  |  | 1 |  | 1 | 0
1733 | planned_characteristic | 3 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_PDM_1 | CR_210_2 | 1 |  | 1 | 0.5
1735 | pre_defined_datum_2d_symbol | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1736 | pre_defined_datum_3d_symbol | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1737 | printed_physical_layout_template | 5 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1740 | requirement_decomposition | 4 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1741 | sequential_laminate_assembly_design | 5 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1744 | discrete_shield | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1747 | specification_document | 4 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_PDM_1 | CR_210_2 | 1 |  | 1 | 0.5
1750 | text_representation | 5 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1751 | test_requirement_allocation | 3 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1752 | thermal_network_definition | 5 | CR_210_2 | CR_210_2 | Publication index ready |  | 1 | Yes | CR11 | CR_210_2 | CR_210_1 | CR_210_2 | 1 |  | 1 | 0.5
1753 | value_with_unit_extension | 4 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1755 | physical_connectivity_definition | 5 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1764 | shape_feature | 4 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1765 | characterizable_object | 3 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1767 | composite_constituent_shape | 4 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1770 | part_and_zone_laminate_tables | 4 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_PDM_1 | CR_composites | 1 |  | 1 | 0.5
1772 | ply_orientation_specification | 3 | CR_composites | CR_composites | In work |  | 1 | Yes | CR11 | CR_composites | CR_PDM_1 | CR_composites | 1 |  | 1 | 0.5
1780 | external_unit | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1788 | explicit_constraints | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1789 | geometric_constraints | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1790 | parameterization_and_variational_representation | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1791 | primitive_solids | 3 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1792 | sketch | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1795 | assembly_feature_relationship | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1796 | kinematic_motion_representation | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1797 | kinematic_structure | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1798 | kinematic_state | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1802 | assembly_component | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1803 | process_plan | 3 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1804 | product_as_individual_assembly_and_test | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1806 | form_feature_in_panel | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1807 | part_shape | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1
1807 | part_shape | 3 | CR_EWH | CR_EWH | In work | ask for new N numbers - Bug 6244 | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 0
1808 | assembly_shape | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1809 | default_setting_association | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1810 | product_and_manufacturing_information_view_context | withdrawn | CR_itemshape_1 | CR_itemshape_1 | Balloted | withdrawn | 1 | Yes | CR11 |  | CR_itemshape_2 | CR_itemshape_1 | 1 |  | 1 | 0
1811 | product_and_manufacturing_information_with_nominal_3d_models | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1812 | product_and_manufacturing_annotation_presentation | 2 | CR_itemshape_2 | CR_itemshape_2 | Submitted to Convener |  | 1 | Yes | CR11 | CR_itemshape_2 | CR_itemshape_2 | CR_itemshape_2 | 1 |  | 1 | 1
1813 | parametric_representation | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1814 | machining_features | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 |  | 1 | CR_PDM_1 | 1 | 0
1815 | mating_structure | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted | Bug 5695 | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1815 | mating_structure | 3 | CR_EWH | CR_EWH | In work |  | 1
1816 | model_based_3d_geometrical_dimensioning_and_tolerancing_representation | 2 | CR_itemshape_1 | CR_itemshape_1 | Balloted |  | 1 | Yes | CR11 | CR_itemshape_1 | CR_itemshape_1 | CR_itemshape_1 | 1 |  | 1 | 1
1819 | tessellated_geometry | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1820 | point_direction_model | 2 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1823 | product_view_definition_reference | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1824 | change_management | 2 | CR_PDM_1 | CR_PDM_1 | Publication index ready |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 | CR_PDM | 1 | CR_PDM_1 | 1 | 0
1826 | physical_connectivity_layout_topology_requirement | 1 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_210_2 | CR_EWH | CR_210_2 | 1 |  | 1 | 0
1827 | extruded_structure_cross_section | 1 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1828 | wiring_harness_assembly_design | 1 | CR_EWH | CR_EWH | In work |  | 1 | Yes | CR11 | CR_EWH | CR_EWH | CR_EWH | 1 |  | 1 | 1
1829 | assembly_module_with_packaged_component | 1 | CR_210_1 | CR_210_1 | Publication index ready |  | 1 | Yes | CR11 | CR_210_1 | CR_210_1 | CR_210_1 | 1 |  | 1 | 1
1830 | edge_based_topological_representation_with_length | 1 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1831 | scan_data_3d_shape | 1 | CR_Geometry | CR_Geometry | Balloted |  | 1 | Yes | CR11 | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 1
1834 | Surface visual texture | 1 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry_2 |  | CR_Geometry_2 | 1 |  | 1 | 0
1836 | Vertex colours for tessellated geometry | 1 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry_2 |  | CR_Geometry_2 | 1 |  | 1 | 0
1844 | General_design_connectivity | 1 | CR_EWH | CR_EWH | In work | ask for new N numbers - Bug 6243 | 1 | [5 empty] | 1 | CR_EWH | 1 | 0
1845 | Wire_and_cable_design_connectivity | 1 | CR_EWH | CR_EWH | In work | ask for new N numbers - Bug 6243 | 1 | [5 empty] | 1 | CR_EWH | 1 | 0
409 | ap209_multidisciplinary_analysis_and_design | 2 | CR_desginAPs_2 | CR_desginAPs_2 | In work | TO REMOVE | 1 | Yes | CR11 | CR_Geometry | CR_209 | CR_composites | 1 |  | 1 | 0
41 | Fundamentals of product description and support (IR) | 5 | CR_IR_41-44 | CR_IR_41-44 | In work | wip - to be frozen in Oslo - pub index to be created | 1 |  |  |  |  | CR_PDM | 1 | CR_P41-P44 | 1 | 0
410 | ap210_electronic_assembly_interconnect_and_packaging_design | 4 | CR_desginAPs_1 | CR_desginAPs_1 | In work |  | 1 | Yes | CR11 | CR_Geometry | CR_210_1 | CR_210_2 | 1 |  | 1 | 0
42 | Geometric and topological representation (IR) | 5 | CR_Geometry | CR_Geometry | Balloted | Related updated schemas : geometric_model_schema, geometry_schema, scan_data_3d_shape_model_schema, topology_schema | 1 |  |  | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 0
42 | Geometric and topological representation (IR) | 6 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 0
43 | Representation structures (IR) | 4 | CR_Geometry | CR_Geometry | Balloted | Related updated schemas : representation_schema | 1 |  |  | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 0
43 | Representation structures (IR) | 5 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 |  |  | CR_Geometry | CR_Geometry | CR_Geometry | 1 |  | 1 | 0
44 | Product structure configuration (IR) | 4 | CR_IR_41-44 | CR_IR_41-44 | In work | wip - to be frozen in Oslo - pub index to be created | 1 |  |  |  |  | CR_PDM | 1 | CR_P41-P44 | 1 | 0
442 | ap242_managed_model_based_3d_engineering | 2 | CR_desginAPs_1 | CR_desginAPs_1 | In work |  | 1 | Yes | CR11 | CR_PDM_1 | CR_PDM_1 |  | 1 | CR_PDM_1 | 1 | 0
442 | ap242_managed_model_based_3d_engineering | 3 | CR_desginAPs_2 | CR_desginAPs_2 | In work | to be added to pub index | 1
46 | visual_presentation | 4 | CR_Geometry_2 | CR_Geometry_2 | In work |  | 1 | [5 empty] | 1 |  | 1 | 0
1847 | Additive_manufacturing | 1 | CR_composites |  | In work | After SMRLv8.7, CR additive ? Right NB | 0 |  |  |  |  | CR_composites | 0 |  | 1 | 0
Totals | Nb of blank cells | 0 | 5 | 6 |  |  |  | 32 | 31 | 21 | 26 | 19
203 | 203 | 203 | 198 | 197 |  |  |  | 171 | 172 | 182 | 177 | 184 |  | 35
Note on J64: no changes since 10 years. Seem to be an error

## pub checks
Final Listings | Pub indexes | CR ID
- | - | -
elemental_geometric_shape | elemental_geometric_shape | CR_Geometry
elemental_topology | elemental_topology | CR_Geometry
value_with_unit | value_with_unit | CR_Geometry
construction_geometry | construction_geometry | CR_Geometry
procedural_solid_model | procedural_solid_model | CR_Geometry
solid_with_local_modification | solid_with_local_modification | CR_Geometry
basic_geometric_topology | basic_geometric_topology | CR_Geometry
geometrically_bounded_surface | geometrically_bounded_surface | CR_Geometry
manifold_surface | manifold_surface | CR_Geometry
advanced_boundary_representation | advanced_boundary_representation | CR_Geometry
product_data_quality_definition | product_data_quality_definition | CR_Geometry
product_data_quality_criteria | product_data_quality_criteria | CR_Geometry
product_data_quality_inspection_result | product_data_quality_inspection_result | CR_Geometry
shape_data_quality_criteria | shape_data_quality_criteria | CR_Geometry
composite_surface | composite_surface | CR_Geometry
basic_geometry | basic_geometry | CR_Geometry
manifold_subsurface | manifold_subsurface | CR_Geometry
constructive_solid_geometry_2d | constructive_solid_geometry_2d | CR_Geometry
composite_constituent_shape | composite_constituent_shape | CR_Geometry
geometric_constraints | geometric_constraints | CR_Geometry
parameterization_and_variational_representation | parameterization_and_variational_representation | CR_Geometry
primitive_solids | primitive_solids | CR_Geometry
sketch | sketch | CR_Geometry
parametric_representation | parametric_representation | CR_Geometry
tessellated_geometry | tessellated_geometry | CR_Geometry
point_direction_model | point_direction_model | CR_Geometry
edge_based_topological_representation_with_length | edge_based_topological_representation_with_length | CR_Geometry
scan_data_3d_shape | scan_data_3d_shape | CR_Geometry
Geometric and topological representation (IR) | geometric_and_topological_representation | CR_Geometry
Representation structures (IR) | representation_structures | CR_Geometry
IR 42 schema | geometric_model_schema | CR_Geometry
IR 42 schema | geometry_schema | CR_Geometry
IR 42 schema | scan_data_3d_shape_model_schema | CR_Geometry
IR 42 schema | topology_schema | CR_Geometry
IR 43 schema | representation_schema | CR_Geometry
- | - | -
product_view_definition | product_view_definition | CR_itemshape_1
assembly_structure | assembly_structure | CR_itemshape_1
contextual_shape_positioning | contextual_shape_positioning | CR_itemshape_1
shape_property_assignment | shape_property_assignment | CR_itemshape_1
product_view_definition_relationship | product_view_definition_relationship | CR_itemshape_1
surface_conditions | surface_conditions | CR_itemshape_1
design_material_aspects | design_material_aspects | CR_itemshape_1
associative_draughting_elements | associative_draughting_elements | CR_itemshape_1
shape_data_quality_inspection_result | shape_data_quality_inspection_result | CR_itemshape_1
extended_geometric_tolerance | shape_feature | CR_itemshape_1
shape_feature | withdrawn | CR_itemshape_1
characterizable_object | characterizable_object | CR_itemshape_1
assembly_component | assembly_component | CR_itemshape_1
assembly_shape | assembly_shape | CR_itemshape_1
default_setting_association | default_setting_association | CR_itemshape_1
product_and_manufacturing_information_view_context | withdrawn | CR_itemshape_1
mating_structure | mating_structure | CR_itemshape_1
model_based_3d_geometrical_dimensioning_and_tolerancing_representation | model_based_3d_geometrical_dimensioning_and_tolerancing_representation | CR_itemshape_1
- | - | -
part_view_definition | part_view_definition | CR_itemshape_2
geometric_tolerance | geometric_tolerance | CR_itemshape_2
product_occurrence | product_occurrence | CR_itemshape_2
derived_shape_element | derived_shape_element | CR_itemshape_2
product_placement | product_placement | CR_itemshape_2
property_as_definition | property_as_definition | CR_itemshape_2
assembly_physical_requirement_allocation | assembly_physical_requirement_allocation | CR_itemshape_2
feature_and_connection_zone | feature_and_connection_zone | CR_itemshape_2
non_feature_shape_element | non_feature_shape_element | CR_itemshape_2
part_external_reference | part_external_reference | CR_itemshape_2
part_feature_function | part_feature_function | CR_itemshape_2
Part template 3d shape | part_template_3d_shape | CR_itemshape_2
kinematic_motion_representation | kinematic_motion_representation | CR_itemshape_2
kinematic_structure | kinematic_structure | CR_itemshape_2
kinematic_state | kinematic_state | CR_itemshape_2
part_shape | part_shape | CR_itemshape_2
product_and_manufacturing_information_with_nominal_3d_models | product_and_manufacturing_information_with_nominal_3d_models | CR_itemshape_2
product_and_manufacturing_annotation_presentation | product_and_manufacturing_annotation_presentation | CR_itemshape_2
- | - | -
assembly_component_placement_requirements | assembly_component_placement_requirements | CR_210_1
assembly_functional_interface_requirement | assembly_functional_interface_requirement | CR_210_1
assembly_module_with_macro_component | assembly_module_with_macro_component | CR_210_1
assembly_module_with_subassembly | assembly_module_with_subassembly | CR_210_1
assembly_module_with_interconnect_component | assembly_module_with_interconnect_component | CR_210_1
assembly_module_with_cable_component | assembly_module_with_cable_component | CR_210_1
assembly_module_with_packaged_connector_component | assembly_module_with_packaged_connector_component | CR_210_1
footprint_definition | footprint_definition | CR_210_1
bare_die | bare_die | CR_210_1
component_grouping | component_grouping | CR_210_1
fabrication_joint | fabrication_joint | CR_210_1
fabrication_technology | fabrication_technology | CR_210_1
interconnect_2d_shape | interconnect_2d_shape | CR_210_1
interconnect_module_to_assembly_module_relationship | interconnect_module_to_assembly_module_relationship | CR_210_1
interconnect_module_usage_view | interconnect_module_usage_view | CR_210_1
interconnect_module_with_macros | interconnect_module_with_macros | CR_210_1
interconnect_physical_requirement_allocation | interconnect_physical_requirement_allocation | CR_210_1
interconnect_placement_requirements | interconnect_placement_requirements | CR_210_1
land | land | CR_210_1
layered_interconnect_module_3d_design | layered_interconnect_module_3d_design | CR_210_1
layered_interconnect_module_design | layered_interconnect_module_design | CR_210_1
layered_interconnect_module_with_printed_component_design | layered_interconnect_module_with_printed_component_design | CR_210_1
layout_macro_definition | layout_macro_definition | CR_210_1
package | package | CR_210_1
packaged_connector_model | packaged_connector_model | CR_210_1
packaged_part_black_box_model | packaged_part_black_box_model | CR_210_1
layered_interconnect_complex_template | layered_interconnect_complex_template | CR_210_1
layered_interconnect_simple_template | layered_interconnect_simple_template | CR_210_1
physical_node_requirement_to_implementing_component_allocation | physical_node_requirement_to_implementing_component_allocation | CR_210_1
physical_unit_2d_shape | physical_unit_2d_shape | CR_210_1
physical_unit_design_view | physical_unit_design_view | CR_210_1
printed_physical_layout_template | printed_physical_layout_template | CR_210_1
test_requirement_allocation | test_requirement_allocation | CR_210_1
assembly_module_with_packaged_component | assembly_module_with_packaged_component | CR_210_1
- | - | -
geometric_model_2d_3d_relationship | geometric_model_2d_3d_relationship | CR_210_2
altered_package | altered_package | CR_210_2
cable | cable | CR_210_2
datum_difference_based_model | datum_difference_based_model | CR_210_2
design_specific_assignment_to_assembly_usage_view | design_specific_assignment_to_assembly_usage_view | CR_210_2
Functional_decomposition_to_design | functional_decomposition_to_design | CR_210_2
part_template | part_template | CR_210_2
physical_unit_2d_design_view | physical_unit_2d_design_view | CR_210_2
Physical_unit_3D_design_view | physical_unit_3d_design_view | CR_210_2
physical_unit_3d_shape | physical_unit_3d_shape | CR_210_2
Physical unit interconnect definition | physical_unit_interconnect_definition | CR_210_2
planned_characteristic | planned_characteristic | CR_210_2
pre_defined_datum_2d_symbol | pre_defined_datum_2d_symbol | CR_210_2
pre_defined_datum_3d_symbol | pre_defined_datum_3d_symbol | CR_210_2
sequential_laminate_assembly_design | sequential_laminate_assembly_design | CR_210_2
discrete_shield | discrete_shield | CR_210_2
specification_document | specification_document | CR_210_2
thermal_network_definition | thermal_network_definition | CR_210_2
- | - | -
approval | approval | CR_PDM_1
work_request | work_request | CR_PDM_1
dimension_tolerance | dimension_tolerance | CR_PDM_1
event | event | CR_PDM_1
product_class | product_class | CR_PDM_1
specification_based_configuration | specification_based_configuration | CR_PDM_1
classification_with_attributes | classification_with_attributes | CR_PDM_1
measure_representation | measure_representation | CR_PDM_1
document_assignment | document_assignment | CR_PDM_1
manufacturing_configuration_effectivity | manufacturing_configuration_effectivity | CR_PDM_1
product_data_management | product_data_management | CR_PDM_1
product_breakdown | product_breakdown | CR_PDM_1
drawing_definition | drawing_definition | CR_PDM_1
draughting_element_specialisations | draughting_element_specialisations | CR_PDM_1
incomplete_data_reference_mechanism | incomplete_data_reference_mechanism | CR_PDM_1
inertia_characteristics | inertia_characteristics | CR_PDM_1
design_product_data_management | design_product_data_management | CR_PDM_1
characteristic | characteristic | CR_PDM_1
generic_material_aspects | generic_material_aspects | CR_PDM_1
text_representation | text_representation | CR_PDM_1
value_with_unit_extension | value_with_unit_extension | CR_PDM_1
external_unit | external_unit | CR_PDM_1
explicit_constraints | explicit_constraints | CR_PDM_1
assembly_feature_relationship | assembly_feature_relationship | CR_PDM_1
process_plan | process_plan | CR_PDM_1
product_as_individual_assembly_and_test | product_as_individual_assembly_and_test | CR_PDM_1
form_feature_in_panel | form_feature_in_panel | CR_PDM_1
machining_features | machining_features | CR_PDM_1
product_view_definition_reference | product_view_definition_reference | CR_PDM_1
change_management | change_management | CR_PDM_1
- | - | -
product_occurrence | product_occurrence | CR_EWH
assembly_module_design | assembly_module_design | CR_EWH
assembly_module_usage_view | assembly_module_usage_view | CR_EWH
assembly_technology | assembly_technology | CR_EWH
component_feature | component_feature | CR_EWH
functional_assignment_to_part | functional_assignment_to_part | CR_EWH
functional_specification | functional_specification | CR_EWH
interface_component | interface_component | CR_EWH
model_parameter | model_parameter | CR_EWH
network_functional_design_view | network_functional_design_view | CR_EWH
functional_usage_view | functional_usage_view | CR_EWH
part_feature_location | part_feature_location | CR_EWH
physical_component_feature | physical_component_feature | CR_EWH
Physical unit usage view | physical_unit_usage_view | CR_EWH
requirement_decomposition | requirement_decomposition | CR_EWH
physical_connectivity_definition | physical_connectivity_definition | CR_EWH
part_shape | part_shape | CR_EWH
mating_structure | mating_structure | CR_EWH
physical_connectivity_layout_topology_requirement | physical_connectivity_layout_topology_requirement | CR_EWH
extruded_structure_cross_section | extruded_structure_cross_section | CR_EWH
wiring_harness_assembly_design | wiring_harness_assembly_design | CR_EWH
General_design_connectivity | general_design_connectivity | CR_EWH
Wire_and_cable_design_connectivity | wire_and_cable_design_connectivity | CR_EWH
- | - | -
ap242_managed_model_based_3d_engineering ed3 | ap242_managed_model_based_3d_engineering
Appearance assignment | appearance_assignment | CR_Geometry_2
construction_geometry | construction_geometry | CR_Geometry_2
constructive_solid_geometry_2d | constructive_solid_geometry_2d | CR_Geometry_2
Surface visual texture | surface_visual_texture | CR_Geometry_2
Vertex colours for tessellated geometry | vertex_colours_for_tessellated_geometry | CR_Geometry_2
Geometric and topological representation (IR) | geometric_and_topological_representation | CR_Geometry_2
Representation structures (IR) | representation_structures | CR_Geometry_2
visual_presentation | visual_presentation | CR_Geometry_2
IR 42 schema | topology_schema | CR_Geometry_2
IR 43 schema | representation_schema | CR_Geometry_2
IR 46 schema | presentation_appearance_schema | CR_Geometry_2
- | - | -
associative_draughting_elements | associative_draughting_elements | CR_PMI_2
dimension_and_tolerance_callouts | dimension_and_tolerance_callouts | CR_PMI_2
mechanical_design | mechanical_design | CR_PMI_2
associative_draughting_elements | associative_draughting_elements | CR_PMI_2
draughting | draughting | CR_PMI_2
AIC 113 schema | mechanical_design | CR_PMI_2
AIC 101 schema | draughting_element_schema | CR_PMI_2
AIC 101 schema | aic_draughting_elements | CR_PMI_2
- | - | -
numeric_function | numeric_function | CR_composites
fea_definition_relationships | fea_definition_relationships | CR_composites
mesh_topology | mesh_topology | CR_composites
numeric_expression | numeric_expression | CR_composites
elementary_function | elementary_function | CR_composites
part_and_zone_laminate_tables | part_and_zone_laminate_tables | CR_composites
ply_orientation_specification | ply_orientation_specification | CR_composites
ap209_multidisciplinary_analysis_and_design | ap209_multidisciplinary_analysis_and_design
Additive manufacturing | MISSING | CR_composites
- | - | -

## Pivot
stepmod pub index | (All)
Lothar Klein listing | (All)
Howard Mason listing | (Multiple Items)
Tom Bluhm listing | (All)
Row Labels
Grand Total

## CR_210-2
Nous | LTK | HM | TB | CR 210-1 | Fully allign
1404 | 1404 | 1404 | 1404 |  | OK
1601 | 1601 | 1601 | 1601 |  | OK
|  |  | 1634 | 1634
|  |  | 1635 | 1635
1638 | 1638 | 1638 | 1638 |  | OK
1639 | 1639 | 1639 | 1639 |  | OK
|  |  | 1640 | 1640
|  |  | 1641 | 1641
|  |  | 1643 | 1643
|  |  | 1644 | 1644
|  |  | 1645 | 1645
|  |  | 1646 | 1646
|  |  | 1650 | 1650
1656
1660 | 1660 | 1660 | 1660 |  | OK
1662 | 1662 | 1662 |  |  | NOK
|  |  | 1668 | 1668
|  |  | 1670 | 1670
1676 | 1676 | 1676 | 1676 |  | OK
|  |  | 1682 | 1682
|  |  | 1685 | 1685
|  |  | 1686 | 1686
|  |  | 1687 | 1687
|  |  | 1689 | 1689
|  |  | 1690 | 1690
|  |  | 1692 | 1692
|  |  | 1696 | 1696
|  |  | 1698 | 1698
|  |  | 1700 | 1700
|  |  | 1701 | 1701
|  |  | 1707 | 1707
|  |  | 1708 | 1708
1709 | 1709 | 1709 | 1709 |  | OK
|  |  | 1710 | 1710
|  |  | 1716 | 1716
|  |  | 1718 | 1718
1722 | 1722 | 1722 |  |  | NOK
|  |  | 1723 | 1723
1725 | 1725 | 1725 | 1725 |  | OK
|  |  | 1726 | 1726
1727 | 1727 |  |  |  | NOK
|  |  | 1728 | 1728
1729 | 1729 | 1729 | 1729 |  | OK
1733 | 1733 |  |  |  | NOK
1735 | 1735 | 1735 | 1735 |  | OK
1736 | 1736 | 1736 | 1736 |  | OK
|  | 1737 | 1737 | 1737
1741 | 1741 | 1741 | 1741 |  | OK
1744 | 1744 | 1744 | 1744 |  | OK
1747 | 1747 | 1747 |  |  | NOK
|  |  | 1751 | 1751
1752 | 1752 | 1752 |  |  | OK
1753 |  |  |  |  | NOK
1826 | 1826 |  |  |  | NOK
|  |  | 1829 | 1829
410 | 410 | 410 | 410 |  | Problème sur l'édition 4 ou 5

## CR_210-2 (2)
Nous | LTK | HM | TB | CR 210-1 | Fully allign
1404 | 1404 | 1404 | 1404 |  | OK
1601 | 1601 | 1601 | 1601 |  | OK
1638 | 1638 | 1638 | 1638 |  | OK
1639 | 1639 | 1639 | 1639 |  | OK
1660 | 1660 | 1660 | 1660 |  | OK
1662 | 1662 | 1662 |  |  | NOK
1676 | 1676 | 1676 | 1676 |  | OK
1709 | 1709 | 1709 | 1709 |  | OK
1722 | 1722 | 1722 |  |  | NOK
1725 | 1725 | 1725 | 1725 |  | OK
1727 | 1727 |  |  |  | NOK
1729 | 1729 | 1729 | 1729 |  | OK
1733 | 1733 |  |  |  | NOK
1735 | 1735 | 1735 | 1735 |  | OK
1736 | 1736 | 1736 | 1736 |  | OK
1741 | 1741 | 1741 | 1741 |  | OK
1744 | 1744 | 1744 | 1744 |  | OK
1747 | 1747 | 1747 |  |  | NOK
1752 | 1752 | 1752 |  |  | OK
1753 |  |  |  |  | NOK
1826 | 1826 |  |  |  | NOK
410 | 410 | 410 | 410 |  | Problème sur l'édition 4 ou 5