## CR_Geometry BZ bug
Type | Type Text | Geometry | Bug | Bug Description | checked if last BZ comments consistent | moved to CR_Geometry milestone | in publication index | collector bug used and checked | stepmod changes done locally | check change history | changes committed and tagged | publication date updated | WG NB updated | push this bug also to CR_Geometry ?
- | Fully Done | 1767 | 4853 | Missing name-attribute in Boundary_curve_representation | yes | yes | yes |  | yes
1 | Partial Detail, Fully Done | 42 | 4861 | Add Curved triangles, update tessellated geometry | yes | yes | yes | yes | yes | yes |  | yes
0 | Not Done | 1386 | 4987 | invalid function call in product_of_mesh.wr1 | not understood | yes | no |  | no
- | Fully Done | 1131 | 5030 | spelling errors in 1131 MIM EXPRESS SELECT types | yes | yes | yes |  | yes
- | Fully Done | 1004 | 5217 | Add extension to identification_item to AM 1004 Elemental_geometric_shape | yes | yes | yes | yes | yes
3 | Complete | 42 | 5409 | Error in description of coordinates_list | yes | yes | yes | yes | yes |  |  | yes
3 | Complete | 1830 | 5434 | New AM edge based topological representation with length | not clear | yes | yes | yes | yes |  |  | yes
3 | Complete | 42 | 5448 | New IR entities edge_with_length, vertex_on_edge, mid_edge_vertex | yes | yes | yes | yes | yes | yes |  | yes
3 | Complete | 42 | 5452 | Geometry schema not compilable | yes | yes | yes | yes | yes | yes |  | yes
3 | Complete | 43 | 5454 | Extend representation_relationship_with_transformation.transformation_operator for several item_defined_transformations | yes | yes | yes |  | yes | yes
- | Fully Done | 1819 | 5458 | AM1819 edition 2 Tessellated geometry | yes | yes | yes | yes | yes
3 | Complete | 1004 | 5465 | Detailed_geometric_model_element does not include new AO Point introduced in SMRLv5/6 | yes | yes | yes | yes | yes |  |  |  |  | 5605
3 | Complete | 1318 | 5509 | Missing USE FROM in MIM | yes | yes | yes |  | yes
d | Dup | 1819 | 5526 | Add Curved triangles, update tessellated geometry (duplicate of 5458) | yes | yes | yes | yes | yes
0 | Not Done | 1831 | 5528 | Add 3D Scan data AM | reopened | yes | yes | yes | in progress
3 | Complete | 1819 | 5550 | Change ARM entity name from Tessellated_anotation to Tessellated_annotation | yes | yes | yes | yes | yes
3 | Complete | 1005, 1110, 1131, 1514, 1323, 1507, 1509, 1520, 1521, 1522, 1523, 1525, 1652, 1702, 1731, 1789, 1790, 1791, 1792, 1813, 1819, 1820 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes
3 | Complete | 1830 | 5595 | Miss AO Subedege | not clear | yes | yes | yes |  |  |  | yes
3 | Complete | 1830 | 5596 | Need Connected_edge_sub_set | yes | yes | yes | yes | yes |  |  | yes
3 | Complete | 1520 | 5630 | Spelling error on select: pqd_organization_item must be pdq_organization_item | yes | yes | yes | list of bugs | yes | yes
1 | Partial | 1819, 1830, 1831 | 5644 | Various ARM-MIM mapping errors on extended selects in AP242E2, AP210 | not closed, to be review in wg21 | yes |  |  | yes |  |  | yes
? | Collector | 1004, 1005, 1319, 1789, 1790, 1819, 1831 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema
3 | Complete | 1386 | 5673 | MESH_TOPOLOGY_SCHEMA used in the ARM
3 | Complete | 1819 | 5677 | Missing cubic_bezier_triangulated_face and cubic_bezier_tessellated_edge
k | reopen | 42 | 5527 | Add 3D Scan data to part 42 | reopened | yes | yes | yes | yes | yes |  | yes
k | reopen | 42 | 5566 | Collector bug for Part 42 Ed 5 for CR11 | reopened | yes | yes | yes | yes | yes |  | yes
k | new | 1830 | 5891 | Collector bug for AM edge_based_topological_representation_with_length | yes | yes | yes | yes | yes |  |  | yes
k | depends | 1004 | 5605 | Collector bug for Part 1004 of AP242ed2 CR 11 | yes | yes | yes | yes | yes