## CR_geometry Bugs and Parts list
Status key | Status | Parts | Bugs | Bug Description | checked if last BZ comments consistent | moved to CR_Geometry milestone | in publication index | bugs in the publication index | stepmod changes done locally | checked if other bugs against this module from CR11 | checked date format | check change history | changes committed and tagged | WG NB updated | publication date updated and
3 | Complete | 42 | 5409 | Error in description of coordinates_list | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
3 | Complete | 42 | 5448 | New IR entities edge_with_length, vertex_on_edge, mid_edge_vertex | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
3 | Complete | 42 | 5452 | Geometry schema not compilable | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | reopen | 42 | 5527 | Add 3D Scan data to part 42 | reopened | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | reopen | 42 | 5566 | Collector bug for Part 42 Ed 5 for CR_Geometry | reopened | yes | yes | collector | yes | yes | yes | yes |  |  | yes
1 | Partial Detail, Fully Done | 42 | 4861 | Add Curved triangles, update tessellated geometry | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | depends | 42 | 5703 | Constraints on subtypes of cartesian_point for polar, spherical and cylindrical | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | depends | 42 | 5650 | part42ed5 COLLECTOR BUG | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | depends | 42 | 5805 | No change annex provided. | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
k | depends | 42 | 5650 | description file for scan_data_3d_shape_model_schema is corrupt and prevent build | yes | yes | yes | collector | yes | yes | yes | yes |  |  | yes
3 | Complete | 43 | 5454 | Extend representation_relationship_with_transformation.transformation_operator for several item_defined_transformations | yes | yes | yes | 2 bugs | yes | yes | yes | yes |  |  | yes
k | depends | 43 | 5806 | No change annex provided. | yes | yes | yes | 2 bugs | yes | yes | yes | yes |  |  | yes
k | new | 409 | 5898 | 409 LF schemas of CR_Geometry | in progress | yes | yes | 1 bug |  |  | NO
k | new | 410 | 5897 | 410 LF schemas of CR_Geometry | in progress | yes | yes | 1 bug |  |  | yes
k | new | 442 | 5896 | 442 LF schemas of CR_Geometry | in progress | yes | yes | 1 bug |  |  | yes
k | depends | 1004 | 5605 | Collector bug for Part 1004 for CR_Geometry | yes | yes | yes | collector | yes | yes | yes
k | depends | 1004 | 5151 | Elemental_geometric_shape_arm interfaces Identification_assignment_arm but fails to extend identification_item | yes | yes | yes | collector | yes | yes | yes
k | dispatched | 1004 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | collector | yes | yes | yes
3 | Complete | 1004 | 5465 | Detailed_geometric_model_element does not include new AO Point introduced in SMRLv5/6 | yes | yes | yes | collector | yes | yes | yes
- | Fully Done | 1004 | 5217 | Add extension to identification_item to AM 1004 Elemental_geometric_shape | yes | yes | yes | collector | yes | yes | yes
k | dispatched | 1005 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 2 bugs | yes | yes | yes
k | dispatched | 1005 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | 2 bugs | yes | yes | yes
k | dispatched | 1110 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes |  |  |  | yes
- | Fully Done | 1131 | 5030 | spelling errors in 1131 MIM EXPRESS SELECT types | yes | yes | yes | 2 bugs | yes | yes | yes
k | dispatched | 1131 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 2 bugs | yes | yes | yes
3 | Complete | 1318 | 5509 | Missing USE FROM in MIM | yes | yes | yes | 1 bug | yes | yes | yes, version 1 was not conformed |  |  |  | yes
k | dispatched | 1319 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1507 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 2 bugs | yes | yes | yes
k | depends | 1507 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | 2 bugs | yes | yes | yes
k | dispatched | 1509 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1514 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
3 | Complete | 1520 | 5630 | Spelling error on select: pqd_organization_item must be pdq_organization_item | yes | yes | yes | list of 2 bugs | yes | yes | yes | yes |  |  | yes
k | dispatched | 1520 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | list of 2 bugs | yes | yes | yes | yes |  |  | yes
k | dispatched | 1521 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1522 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | no bz compo | yes
k | dispatched | 1523 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1525 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1652 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1702 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1731 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
- | Fully Done | 1767 | 4853 | Missing name-attribute in Boundary_curve_representation | yes | yes | yes | collector | yes | yes | yes
k | depends | 1767 | 5653 | Collector bug for Part 1767 for CR_Geometry | yes | yes | yes | collector | yes | yes | yes
k | depends | 1767 | 4914 | Option of tessellated_shape_representation missing | yes | yes | yes | collector | yes | yes | yes
k | dispatched | 1789 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | list of 2 bugs | yes | yes | yes
k | dispatched | 1789 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | list of 2 bugs | yes | yes | yes
k | dispatched | 1790 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | list of 2 bugs | yes | yes | yes
k | dispatched | 1790 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | list of 2 bugs | yes | yes | yes
k | dispatched | 1791 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1792 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
k | dispatched | 1813 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | 1 bug | yes | yes | yes
- | Fully Done | 1819 | 5458 | AM1819 edition 2 Tessellated geometry | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
d | Dup | 1819 | 5526 | Add Curved triangles, update tessellated geometry (duplicate of 5458) | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
3 | Complete | 1819 | 5550 | Change ARM entity name from Tessellated_anotation to Tessellated_annotation | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
3 | Complete | 1819 | 5677 | Missing cubic_bezier_triangulated_face and cubic_bezier_tessellated_edge | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | depends | 1819 | 5623 | Collector bug for Part 1819 for CR_Geometry | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | dispatched | 1819 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | new | 1819 | 5900 | AM 1819, 1830, 1831 ARM-MIM mapping errors on extended selects for CR_Geometry | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | dispatched | 1819 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | dispatched | 1820 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes | yes | yes | collector | yes | yes | yes
3 | Complete | 1830 | 5434 | New AM edge based topological representation with length | not clear | yes | yes | collector | yes |  | yes |  |  |  | yes
3 | Complete | 1830 | 5595 | Miss AO Subedege | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
3 | Complete | 1830 | 5596 | Need Connected_edge_sub_set | yes | yes | yes | collector | yes |  | yes |  |  |  | yes
k | new | 1830 | 5891 | Collector bug for AM edge_based_topological_representation_with_length | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
k | new | 1830 | 5900 | AM 1819, 1830, 1831 ARM-MIM mapping errors on extended selects for CR_Geometry | yes | yes | yes | collector | yes | yes | yes |  |  |  | yes
0 | Not Done | 1831 | 5528 | Add 3D Scan data AM | reopened, updated locally | yes | yes | 3 bugs | yes | yes | yes |  |  |  | yes
k | new | 1831 | 5900 | AM 1819, 1830, 1831 ARM-MIM mapping errors on extended selects for CR_Geometry | yes | yes | yes | 3 bugs | yes | yes | yes |  |  |  | yes
k | dispatched | 1831 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes | yes | yes | 3 bugs | yes | yes | yes |  |  |  | yes

## Moved out from initial list
3 | Complete | 1005, 1110, 1131, 1514, 1323, 1507, 1509, 1520, 1521, 1522, 1523, 1525, 1652, 1702, 1731, 1789, 1790, 1791, 1792, 1813, 1819, 1820 | 5554 | #50 Various ARM-MIM mapping errors in actual AP242ed2-CD build | yes
1 | Partial | 1819, 1830, 1831 | 5644 | Various ARM-MIM mapping errors on extended selects in AP242E2, AP210 | not closed, to be review in wg21, create a new bug for this 3 modules ?
? | Collector | 1004, 1005, 1319, 1789, 1790, 1819, 1831 | 5662 | Collector STEP Tools Express Checker on AP242ed2 long form schema | yes
0 | Not Done | 1386 | 4987 | invalid function call in product_of_mesh.wr1 | not against 1386 but p52 | yes | no | 2 bugs | no |  | yes
3 | Complete | 1386 | 5673 | MESH_TOPOLOGY_SCHEMA used in the ARM | yes | yes | yes | 2 bugs | yes | yes | yes

## Legend
Legend | meaning
k | added by Kevin compared to initial T. Bluhm list
new | created specifically for CR_Geometry
depends | this line has been added bicause its bug is directly related to one or several of the initial list bugs and is considered as relevant to be included in CR_Geometry
dispatched | coming from collector bugs row (set of modules related to one bug), so created one dedicated row to better manage the status of progress of the CR
reopen | reopen as not yet solved in this new CR